## Slide 1: Portable Ultrasound Device for Coda-Wave Interferometry Sprint 2
Prepared by Michael Kisellus, Christopher Coppedge, Leyton Foxworthy, Matthew Baker, Kyle Fox
27OCT2023

## Slide 2: What is this projects goal?
Produce a handheld ultrasound inspection device for inspecting a bridge/structural component for faults in the field.
This handheld unit gathers and stores test data collected over time 72 hours.
Budget - $2000
Existing commercial solution:
Expensive ($5200)
Is not able to record without an operator present

## Slide 3: Background:
Civil engineering lab has a concrete “scanning” process that involves measuring how ultrasonic waves travel through the concrete

## Slide 4: Background:
Data analysis (through MATLAB) is able to reveal imperfections in the concrete.
Scan of a proper piece of concrete
Scan of a compromised piece of concrete

## Slide 5: Overview of previous sprint (background)
Coordinating with client to understand scope of project
Division of responsibilities
Preliminary design
Establish budget and parts list
Research parts/ data sheets
SRS, SDS, Test Plan

## Slide 6: Progress compared to previous sprint (Work completed)
Electrical system design completed.
Changed: MOSFETS, and added a discharge loop for capacitor.
Cooling system
Software
Tx and Rx system
Control system
Enclosure system

## Slide 8: Current Status
Electrical system design complete and waiting for parts.
Cooling system
Software
Tx and Rx system
Control system
Enclosure system

## Slide 9: Roles of the Team Members
Michael Kisellus: Electrical system, SDD,SRS
Christopher Coppedge: Enclosure system, parts and acquisition
Leyton Foxworthy: Software
Matthew Baker: Cooling system
Kyle Fox: Tx and Rx system, Control system

## Slide 10: Preview of next sprint goals (Work remaining)
Order/ receive parts
Test components individually
Assemble parts into designed system
Program control systems
Test systems per test plan
Troubleshoot as required

## Slide 11: Risks or Issues
Part delay of 30 days for 12v to 500v DC to DC converter
High voltage 500V DC present in system. Client requests instructor permission prior to working on the 500 v section.

## Slide 12: Visual Demo (video recording, live demo, etc.)
N/A

## Slide 13: Questions?